## Sheet1
Task | Description | Start Date | End Date
Preparing PDM Plan | Working on Presentation of PDM plan and Word document to submit on Canvas. Doing Literature Reviews to Research Methods to implement in my project. Making sure that chosen data follows the ethical standards of UoH. | 2024-10-10 | 17/10/2024
Presentation of PDM plan | Present the Prepared PPT to the supervisor and submit the PDM plan report in Canvas. | 18/10/2024 | 18/10/2024
Data Preprocessing - Part 1 | Filling in Missing Values wherever possible, Removing Duplicate Records,Normalizing the Data,Encoding the Data. | 17/10/2024 | 30/10/2024
Data Preprocessing - Part 2 | Using Resampling Techniques and Adjusting Class weights to handle the Imbalanced Target Variable | 24/10/2024 | 2024-06-11
Exploratory Data Analysis (EDA) | analyzing the dataset's characteristics through visualizations and statistical techniques to uncover patterns, and gain insights to help Data Pre-processing if there are any further imbalances. Write the Document about Data Preprocessing and EDA | 31/10/2024 | 13/11/2024
Methodology and Choosing Models to Use | Making plan what are the models we are going to use. For Now, Planning to use 6 Models | 2024-07-11 | 20/11/2024
Data Ethics Quiz | Attempt the Data Ethics Quiz on Alloted Time | 21/11/2024 | 21/11/2024
Implementing Models - Part 1 | Train the 3 Chosen models among 6 Models and tune hyperparameters for the Best Performance. Write the Documentation about these three models. | 14/11/2024 | 27/11/2024
Implementing Models - Part 2 | Train the other 3 models and tune hyperparameters for the Best Performance. Compare all the models performance to see which models working Better.Write the Documentation about these three models. | 21/11/2024 | 2024-04-12
Ensemble Modeling | Do the Ensemble of best performing 3 models and check if it is performing best or not. | 28/11/2024 | 2024-11-12
Plotting the Results | Plot the Performance metrics of all the Models for better understanding and Visualizations. | 2024-12-12 | 25/12/2024
Final Model Refinement & Documentation | Decide on Best models and Write report Results and Conclusion Parts. | 19/12/2024 | 2025-01-01
Finalising the Documentation | Do the Final Checks if everything is included as per the requirements. Check for plagiarism and do the changes if there are any needed. | 26/12/2024 | 2025-01-01
Buffer Time | If there are any changes Recommended by the Supervisor , then this Buffer time helps to do the changes to avoid last minute rush | 2025-02-01 | 2025-07-01
Report Submission | Last date to submit the Report. | 2025-08-01 | 2025-08-01
Preparation for Viva | Prepare for Viva to answer the questions as per the report and the results. Prepare Confidently to present better. | 2025-07-01 | 21/1/25